## 1 Introduction
SIA BluePrint V.1
Last Updated: | 2024-05-17
SIA BluePrint is a dynamic document detailing the essential services that architects generally provide, organized into three main categories: Design Expertise, Contract Administration, and Compliance & Liabilities. This framework aids in the effective allocation of time, resources, and manpower, enhancing project efficiency and facilitating smoother adjustments during the contract. It also highlights potential liabilities, enabling all parties to manage risks more effectively. By promoting transparency of services through the BluePrint, stakeholders are better equipped to make informed decisions. This fosters innovation by granting access to specialized services beyond the core offerings.
For Architects
Architects are encouraged to use the BluePrint as a template for planning the core scope of services offered, as well as for determining the time, resources, and manpower to allocate to each service component. Utilizing the common terminology within the BluePrint can facilitate smoother communication and collaboration with clients and stakeholders throughout the project lifecycle. Additionally, architects can use the BluePrint to identify opportunities for offering specialized services beyond the core, thereby enhancing their competitive position.
Go To BluePrint Listing >
The Terms and Conditions for accessing and using the SIA BluePrint are outlined in the website below. By accessing or using this tool, you are indicating that you agree to be bound by these Terms and Conditions.
website address here
Singapore Institute of Architects

## 2 BluePrint_Design
Task | Stage | Component | Relevant Authority | Remarks | Contract. Admin | Compliance . Liabilities | Biz Ops | Design | RESOURCES
[9 empty] | Director | Senior Associate | Associate | Senior Architect | Architect | Architectural Executive | BIM Manager | BIM Coordinator | BIM Modeller | Technical Executive
DESIGN EXPERTISE | [9 empty] | A
Brief Preparation | Pre-Design | Brief Preparation |  | Assist Client in preparation of Design Brief
| Pre-Design | Consultant Team Recommendations |  | Assemble Consultant Team based on Project and Regulatory Requirements
| Pre-Design | Consultant Team Service Agreements |  | Determine methods of engagement of other consultants
| Pre-Design | Special Project Screening |  | Address project needs such as personnel background checks and secure file storage.
| Pre-Design | Communication Protocol |  | Determine methods, frequency and points of contact for project communication
Concept-Schematic Design Development | Concept - Schematic | Budget Estimation |  | Support the quantity surveyor (QS) with preliminary cost estimation
| Concept - Schematic | Timeline Estimation |  | Provide a preliminary timeline estimation, covering the entire process from design to construction, and define what constitutes a delay/prolongation for design consultants.
| Concept - Schematic | Site Schematic Design Analysis |  | Physical Site Investigation for feasibility
| Concept - Schematic | Design Development |  | Develop the design to a sufficient level of detail for Concept Design – up to the Design Sign Off
| Concept - Schematic | Design Development |  | Develop the design to a sufficient level of detail for Schematic Design - up to the Design Sign Off
| Concept - Schematic | Coordination |  | Coordinate/ Deconflict for integration into design: - Client’s various departments/ seniorities - Other consultants and specialists - Stakeholders - The public
Schematic Design Development | Schematic Design | Design Development |  | Develop the design to a sufficient level of detail for Schematic Design, ensuring key feasibility areas are considered - up to the Design Sign Off
| Schematic Design | Coordination |  | Coordinate/ Deconflict for integration into design: - Client’s various departments/ seniorities - Other consultants and specialists - Stakeholders - Public
| Schematic Design | Update Timeline Estimation |  | - Overall estimation from design to construction - note to keep to orginal contracted timeline, prolongation or delay to highlight to client
Detail Design Development | Detail Design | Design Development |  | Develop the design to a sufficient level of detail for Detail Design - Enough to go into tender preparations - up to the Design Sign Off
| Detail Design | Coordination |  | Coordinate/ Deconflict for integration into design: - Client’s various departments/ seniorities - Other consultants and specialists - Stakeholders - Public
| Detail Design | Update Cost Estimation
| Detail Design | Update Timeline Estimation |  | More detailed estimation for Construction Timeline
Tender Design Development | Tender Preparation | Design Development |  | Develop the design to a sufficient level of detail for Tender - up to the Tender Sign Off
| Tender Preparation | Coordination |  | Coordinate/ Deconflict for integration into design: - Client’s various departments/ seniorities - Other consultants and specialists - Stakeholders - Public
Design Development during Construction | Construction | Review shop drawings |  | Review from design perspective in relation to design intent
| Construction | Coordination |  | Develop the design to a sufficient level of detail for Tender - Until Tender Sign Off
| Construction | Regular Site Review |  | Conduct periodic site reviews to ensure alignment with the design
As Built Verification | Post Construction | Verify as built |  | Verify that construction adheres to the design specifications
| Post Construction | Handover, DLP |  | Cheeck and verify defects
Specialty |  | Expertise in Specific Area |  | E.g.: Heritage Conservation PPVC Green Buildings Mega Scale Healthcare Airport Large Scale Factories Hospitality TOD
Creativity and Branding
Collaboration & Collaboration |  |  |  | Consultants involved may include: Mechanical Engineer, Electrical Engineer, C&S Engineer, DFS, ESD, Façade, Acoustic, Landscape, Arborist, ABC Specialist, Signage, FSE, Traffic Consultant, Lighting, QS, Blast Consultant, Security Consultant, Real Estate Analyst, Conservation, Interior Designer, Industrial Process Engineers, IT, AV, Coastal Engineer, Stage Consultant, Kitchen Specialist, Medical Planner, EIA, and many more. |  | Liabilities of Sub-Consultants under LC
Value Engineering |  |  |  | Redesigning based on design intent

## 3 BluePrint Contract
Task | Stage | Component | Relevant Authority | Remarks | Contract. Admin | Compliance . Liabilities | Biz Ops | Design | RESOURCES
CONTRACT ADMINISTRATION | [8 empty] | Director | Senior Associate | Associate | Senior Architect | Architect | Architectural Executive | BIM Manager | BIM Coordinator | BIM Modeller | Technical Executive
Choosing a Contract (Client-Contractor) | At Services Engagement | General Contract |  | Prepare project contract (Between Client-Contractor): - PSSCOC, SIA, REDAS, FIDIC, NEC4 etc. - Type of Contract: Traditional, D&B, etc.
| At Services Engagement | Early Contractor Involvement (ECI) |  | Allocate manhours for ECI review, pre-tender preparations/drawings, etc.
| At Services Engagement | Contract Parcellation |  | Define phases and stages, including the architect's role
Service Agreement Proposal (Client-Architect) | At Services Engagement | Deciding on components of a Service Agreement |  | Client-Consultant contract details: - Fee model: Percentage vs. Lump Sum - Design only or includes Contract Administration - Fee components: Basic vs. Additional/ Special Services - Payment Schedule, Payment Stages - what are your exclusions? - Disbursement, expenses with admin fee - Definition to change of contract - Copyright - Dispute settlement, Termination - Liability - Clarity on phasing and scope of procurement (i.e. number of packages)
| At Services Engagement | Coordination of Contract |  | - Specify Client’s responsibilities - Determine the parties expected to be involved for contract - Establish the level of responsibility between Architect and consultants/ sub-consultants
| At Services Engagement | Scoping Parts |  | Parcellation of contract packages - Expected number of NSC/ DSC/ Direct Contractor(s)
| At Services Engagement | Technical Requirements |  | Determine BIM submission requirements, including the level of detail (4D BIM, FM BIM, etc.), and compliance with Corenet X.
| At Services Engagement | Client Engagement |  | Understand client expectations and client profile
Tender Preparation | Tender | Contractor Qualifying Methods |  | Determine qualifying methods - Pre-qualification, invitation, or open tendering. Determine selection criteria: Price first, Quality first, or PQM
|  | Scoping Tender Price |  | Determine contingency sum, provisional sum, and prime cost
|  | Advanced Info Package |  | Determine if an advanced info package is required and the scope involved
|  | Preliminaries |  | Possible Preliminaries - Scope of works - Site related - Phasing - Employer specific requirements - Schedule of mock-ups - Subcontracting - BIM requirements (BIM dimensions, Digital Twin, etc) - Labour Considerations
|  | General Specifications & Particular Specifications |  | Vet contract terms
Architectural Specifications
Drawings & BIM model
Tenders for Designated SC
|  | Allocation of Contract Sum |  | Discuss Provisional Sum, Contingency Sum and Prime Cost Discuss Retention Monies, Liquidated Damages, Contractor's P&A, Performance Bond
|  | Coordination of Contract |  | Coordinate requirements from all parties involved or affected by the contract
Contract Construction | Construction: Contract Administration | Verification and Certification of Work |  | Manage required certifications
|  | Assessment of Variation |  | Manage scope, disputes, verification of Variation
|  | Review of Project Duration |  | Monitor EOT, program, and progress, including catch-up programs and microprogram monitoring
Direction/ Instruction
|  | Coordination of Contract |  | Coordinate requirements from all parties involved or affected by the contract
| Construction: Site Inspection | Review of Setting Out
Review of manpower histogram
Review of weekly/ monthly report
Review of RFA/ RFI
Tenders for Designated SC
Review of Subcons/ NSC/ DSC
Review of Mock Ups and Factory Visits
Regular site inspection
|  | Regular site meetings |  | Schedule progress and technical meetings, and determine their regularity
Contract Substantial Completion | Contract Administration | Issuance of Certification
|  | Review of As-Builts |  | Prepare as-built drawings, OMM, and material card sheets. Conduct site walks and verification
Review Defects and Outstanding Works
|  | Site Handover |  | Facilitate site handover between contractor and client.
|  | Coordination of Contract |  | Coordinate requirements from all parties involved or affected by the contract
Contract Full Completion | Contract Administration | Issuance of Certification
|  | Review of As-Builts |  | Prepare as-built drawings, OMM, and material card sheets. Conduct site walks and verification
|  | Coordination of Contract |  | Prepare as-built drawings, OMM, and material card sheets. Conduct site walks and verification
Closure of Contract | Contract Administration | Finalisation of Account |  | Manage: - Final Accounts (Payments) - Variation Orders - Extension of Time - Dispute Resolution - Defects Completion

## 4 BluePrint_Compliance
Task | Stage | Component | Relevant Authority | Remarks | Contract. Admin | Compliance . Liabilities | Biz Ops | Design | RESOURCES
COMPLIANCE & LIABILITIES | [8 empty] | Director | Senior Associate | Associate | Senior Architect | Architect | Architectural Executive | BIM Manager | BIM Coordinator | BIM Modeller | Technical Executive
Compliance Check | Pre-Design | Site Schematic Compliance |  | Conduct pre-design research on regulatory requirements Purchase site information pre-design, including: - Topographical survey, site drawings, DIP, SIP, RLP, and services plan.
Compliance Check | Pre-Submission | Planning requirements | URA | Assess zoning, plot ratio, allowable GFA, and allowable height. Obtain outline approval, change of use, and pre-application consultation as needed If required, submit outline permission to test feasibility
|  | Bonus/ Exemption/ Incentives | URA | Consider bonus scheme requirements (Built Environment Transformation Scheme)
|  | Conservation | URA | Develop relevant conservation and monument plans
|  | Development charges | SLA | Estimate/Calculate Land Betterment Charge (LBC) rates
|  | Engagement of public | URA | Develop a public communications plan (PACs)
|  | Planning requirements (Key projects) | URA | Engage with the Design Advisory Panel
|  | Land Owner's Consent | HDB, JTC, SLA, etc | Plan consent submission for land owner's consent
|  | Planning requirements (Land Owner Urban Design) | JTC | Engage with the Design Review Panel
|  | Planning requirements | URA | Address green buffer, road category, and adjacent developments
|  | Planning requirements | PUB | Ensure setbacks from drainage reserves and sewerage setbacks from public sewer corridors
|  | Planning requirements | LTA | Consider MRT reserve lines, bus stops, traffic crossings, and existing ingress/egress points.
|  | Traffic | LTA | Conduct a Transport Impact Assessment (TIA), if required
|  | Planning requirements (Carparking) | LTA | Determine the number of parking spaces required for each programme type and pre-consult on mechanized parking proposals
|  | Planning requirements (Linkages) | LTA | Plan for new or relocated pedestrian bridges, second-level link bridges, or underground linkages Develop a Walking and Cycling Plan (WCP) report
|  | Change of Use/ En-Bloc | LTA | Consult on the need for a Pre-Application Feasibility Study
|  | Planning requirements (Special) | MHA | Identify requirements for special screening zones and blast protection for public infrastructure buildings
|  | Planning requirements | NParks | Address green buffer, tree conservation areas, and heritage roads. Provide open space for landed housing development. Lodge compliance for open-air carparks
|  | Planning requirements | NEA | Apply for Environmental Information Application and adhere to NEA-required setbacks from various types of pollution
|  | Planning requirements (Special) | NEA | Conduct Environmental Impact Study (EIS-Pre). Assess energy efficiency opportunities (EEOA) for new ventures. Perform Environmental Site Assessment (ESA). Conduct Noise Impact Assessment (NIA-Pre) for traffic. Perform Pollution Control Study (PCS), considering special requirements for pollutant-generating projects. Conduct Quantitative Risk Assessment (QRA)
|  | Licensing/ Operation matters: To cooperate on requirements that will impact design and compliance | MOE | Educational facilities
|  |  | MCYS | Childcare, elderlies
|  |  | NEA | Food establishments
|  |  | SFA | Food related projects
|  |  | MOM, SPF | Dormitories
|  | Pre-consultation and consideration | SCDF | Verify purpose group and building setbacks and the location of public hydrants
|  | Planning requirements (Setback & Height) | DSTA & CAAS | Consider flight path restrictions
|  | Site verification | SLA | Conduct a cadastral survey plan to verify site boundaries and land area Obtain the title deed to verify ownership, leasehold, and check for easements or covenants imposed on the land
|  | Coordination between Authorities |  | Resolve conflicts between agencies
|  | Coordination between Consultants |  | Coordinate inter-disciplinary efforts between consultants
|  | Client Communication |  | Review Concept Design, Costs, Regulatory Issues with Client
|  | BIM |  | Create a BIM Execution Plan (BEP) Construct a BIM model Coordinate on the BIM model with all relevant parties for clash detection, design resolution, and compliance checks Integrate the BIM model for submission
Compliance Check | Design Gateway | Design requirements | URA | Approval for URA Planning Permission (PP) and Written Permission (WP): - Ensure compliance with planning parameters. - Design treatment and screening of M&E, carpark, etc.
|  | Design requirements (Accessibility) | URA | Develop a Walking and Cycling Plan. Detail access to the site and connectivity, including pedestrian, cycling, vehicular, and service access. - Through Block Link (TBL), Underground Pedestrian Link (UPL), Elevated Pedestrian Link (EPL), Covered Walkways (CW), Open Walkways (OW), Covered Linkways (CL), High Covered Linkways (HCL). Ensure corridor width for access within the building.
|  | Design requirements (Green & Sustainability) | URA | Address LUSH requirements. Conduct Environmental Impact Assessment (where required)
|  | Design requirements (Residential) | URA | Design and locate the attic in relation to strata units. Plan balcony screening for balconies, private enclosed spaces, private roof terraces, and indoor recreation spaces. For residential buildings: Share value apportionment
|  | Design requirements (Strata) | URA | Building/ Unit Layout: Assess unit/floor layouts, including strata areas/voids and unit breakdown by type/size
|  | Design requirements (Connectivity) | LTA R&T | DC approval: - Road vesting and location of ingress and egress. - Connection to public walkways and last-mile connection scheme. - For en bloc projects, submit a Pre-Application Feasibility Study (PAFS). - Check the necessity for construction within the road structure safety zone.
|  | Design requirements (Parking) | LTA VP | Determine the number of parking lots for cars, lorries, bicycles, motorcycles, and electric charging stations. Ensure clearances for widths, heights, and turns. Plan for a mechanized parking system if necessary
|  | Design requirements (Rail) | LTA rail and MRT | Consider proximity to MRT tunnels and viaducts
|  | Design requirements | BCA | Address Universal Design and accessibility considerations Address Approved document considerations. Develop a Project Productivity Plan - Obtain In-Principle Approval for such a plan Conduct household/storey shelter pre-consultations Address design for maintainability considerations
|  | Design requirements (Fire) | SCDF | Ensure compliance of household/storey shelters with BCA submission Conduct pre-consultations for waivers
|  | Design requirements (Sewerage and Drainage) | PUB | Pre-consult on roadside drain capacity, sewers, and drainage. Establish MPL and crest level. Plan for sewerage or drainage diversion if required, and propose new sewerage systems and connections.
|  | Design requirements (Environmental Health) | NEA Environmental Health | Consider NEA COPEH: - Public toilets, food outlets, markets, factories, swimming pools, storage of chemicals, and cooling tower setbacks. - Plan the location and setback distance of cooling towers. - Conduct Noise Impact Assessment.
|  | Design requirements (Refuse) |  | Consider NEA COPEH: - Ensure refuse truck clearances and swept path analysis. - Determine the location and size of the bin centre/refuse room/bin point, refuse chute, and recycling chute. - Calculate total daily/two-day refuse output (Litres/day). - Develop a pneumatic waste conveyance system (PWCS) schematic plan.
|  | Design requirements (Industry & Pollution) | NEA Pollution Control | - Industrial Allocation - Plan the orientation and location of nuisance sources (e.g., cooling towers, chiller plants, air handling units, air conditioning condensers, fresh air intake, exhaust outlets). - Ensure nuisance buffer setbacks according to building type, surrounding usage, and transport-related infrastructure. - Plan the location of chimneys and meet BHC and MCH requirements. - Adjust the location for storage of inventory products of concern (e.g., chemicals, oil, fuel). - Plan for changes in industrial processes or production activities. - Plan for changes in existing activities, expansion of existing activities, or proposed new activities. - Conduct noise readings from M&E equipment near category 1 roads. - Plan for effluent treatment. - Conduct Environmental Impact Assessment (EIA) and publish if needed. - Meet height limit and building setback requirements in addition to URA standards.
|  | Design requirements (Landscape & Sustainability) | NParks | Conduct pre-submission consultation of requirements for Greenery Provision and Conservation of Trees Conduct Biodiversity Impact Assessment or assess and reduce biodiversity under URA's EIA framework if required. Develop a planting scheme within the development boundary, including type and number of external plants affected.
|  | Safety | WSH DFS | DFS Guide 1
|  | Design requirements (Facade) | MINDEF | Glazing control
|  | Design requirements (Height) | CAAS | Height control
|  | Design requirements (Special) | MHA | Special Buildings: Plan for Security By Design
|  | Design requirements (Special) | SPF | Ensure compliance for buildings with special requirements (e.g., dormitories).
|  | Development Charges | SLA | Estimate/Calculate of Land Betterment Charge (LBC) rates
|  | Coordination between Authorities |  | Resolve conflicts between agencies
|  | Coordination between Consultants |  | Coordinate inter-disciplinary efforts between consultants
|  | Client Communication |  | Review Concept Design, Costs, Regulatory Issues with Client
|  | BIM |  | Coordinate the BIM model with all relevant parties for clash detection, design resolution, and compliance checks. Integrate the BIM model for submission
Compliance Check | Construction Gateway | Design requirements | BCA | - BP Plan - Accessibility - Approved Document - BScore - Green Mark - Design for Maintainability - Universal Design - Resi: HS/ SS clearance - PPVC: BIP approval
|  | Design requirements (Sustainability) | BCA | Sustainability - Air-Tightness and Leakage - Building Energy Performance (e.g. Plant efficiency, Air distribution efficiency, Total System Efficiency, Lighting system performance etc) where applicable - Measurement and Verification (M&V) Instrumentation - Electrical Submetering - Maintenance of Building Cooling System Performance - Carbon Reduction Measures, including Resource Efficiency Measures such as CUI , Embodied Carbon etc.
|  | Design requirements (Sustainability) |  | Sustainability Special Considerations - Major energy use change during operation - Periodic energy audit during operation
|  | Signage |  | Signage - License for Outdoor Advertising Sign or Signboard
|  | Building Name | URA | - Clearance for building name from Street & Building Naming Board (SBNB)
|  | Address | IRAS | - Approval for housing number and address
|  | Design requirements (Residential) | URA | - Resi: Sale License - Resi: Lodgement to Controller of Housing
|  | Design requirements (Fire) | SCDF | - NOA - Fire Safety Report
|  | Design requirements (Sewerage & Drainage) | PUB | - Collaboration with C&S for drainage and minor sewerage - Collaboration with Mech QP for sanitary lines - Clearance for details of flood protection measures - Clearance to commence work within sewer protection zone - Clearance for earth control measures (C&S)
|  | Design requirements (Refuse) | NEA Environmental Health | - Refuse output - Details of bin centre design, type of refuse compactor
|  | Design requirements (Industry & Pollution) | NEA Pollution Control | - Orientation and location of nuisance sources ((e.g. cooling towers, chiller plants) - Obtain specialist detail for treatment of pollutants and effluent treatment - Storage of specialist chemicals, oils, fuels etc. - Changes to existing approved industrial process and activities
|  | Design requirements (Roads) | LTA R&T | - Culvert, kerbs, tactile, street lighting (with C&S) - Street works deposit, if any (with C&S)
|  | Design requirements (Parking) | LTA VP | - Parking details
|  | Design requirements (Rail) | LTA rail and MRT | - Compliance to LTA’s Code of Practice for Railway Protection / Guidebook for Carrying Out Modification Work to Rapid Transit System (RTS) Stations or Railway by Private Developer '- Vibration and construction control - Clearance for working within rail protection zone
|  | Safety | WSH DFS | DFS Guide 2
|  | Strata | SLA | - Clearances on strata division/ subdivision
|  | Coordination between Authorities |  | - To resolve conflicts between agencies
|  | Coordination between Consultants |  | - Inter-disciplinary coordination
|  | Client Communication |  | - Review Concept Design, Costs, Regulatory Issues with Client
|  | BIM |  | - Coordinate on BIM model with all relevant parties: Clash detection, design resolution, compliance checks - Integrate BIM model for submission
Compliance Check | Construction Stage Stage (Pre-TOP) | Regular Site Inspection for compliance |  | - Duty to highlight and request for rectification of non-compliances
Compliance Check | CorenetX: Completion | Clearance requirement (Planning) | URA | - Amendment plan approval - Clearance on completed LRA - Land/Strata Subdivision and Amalgamation
|  | Clearance requirement (HS/SS) | BCA & SCDF | - HS/ SS commissioning checklist with as-built photo
|  | Clearance requirement | BCA | - Submission of approved Amendment plan/ Record Plan
|  | Clearance requirement (Buildability) | BCA | - As built buildability score
|  | Clearance requirement (Sustainability) | BCA | - As built green mark score
|  | Clearance requirement (Facade) | BCA | - Confirmation of compliance with glazing control requirements, or outside glazing control zone - Declaration of reflectance on facade and roof per Approved Doc Building Envelope - ETTV, RTTV, RETV
|  | Clearance requirement | BCA | Requirements of Approved Doc: - Declare glass barrier laminated - Declare glass at height - Declare good practises suspended ceiling - Headrooms and ceiling heights - Safety from falling, safety from injury from vehicles (bollards)
|  | Clearance requirement (Acccessiblity) | BCA | Accessibility Requirements: - Access to and within Site
|  | Clearance requirement | BCA | - Certificate of cable readiness
|  | Clearance requirements (Cable) | IMDA | - Check commissioning of master antennae television system - Check if any 4G antennae networks
|  | Clearance requirement | BCA | Buildability Design Implementation Plan (BDIP)
|  | Clearance requirement (Residential) | BCA | Dwelling Units: - Bathrooms for future retrofitting - Design of unit entrance for wheelchair users
|  | Clearance requirement (Fire) | SCDF | TFP Application: - RI inspection - FSSD approved plans - Notice of approvals - Fire rated certificates - Declaration of compliance - Special material forms - Record of issue of fire door labels - Record of issue of lift door labels
|  | Clearance requirement | LTA R&T | Amendment plan if required
|  | Clearance requirement | LTA VP | Amendment plan if required
|  | Clearance requirement | LTA Rail | Amendment plan if required
|  | Clearance requirement (Sewerage and Drainage) | PUB | - As built with crest level, MPL, flood protection level - Obtain water turn on, bulk meter in operatoin - Licensed plumber inspection - CCTV survey of sewers - Transfer of management of pumped drainage system - Oversee M&E obtain sewer and drainage TOP clearances
|  | Clearance requirement (Environmental Health) | NEA EH | - Bin centre completion with manoeuvring space and loading/ unloading of bin - EH TOP - Noise instrument report
|  | Clearance requirements (Industry & Pollution) | NEA PC | - Post construction noise assessment report： - Noise Impact Assessment (NIA-Post) for Land Traffic Noise - Noise Report for ACMV - Pollution Control Equipment (PCE): Required for developments involving proposed PCE/fuel burning equipment (e.g. Boiler, Thermal Oxidiser, Scrubber, Dust Collector, Spray Paint Booth, etc.) - PC TOP
|  | Clearance requirements (Landscape & Sustainability) | NParks | Amendment plan if required
|  | Clearance requirements (Electrical) | SP | - Commission and hand over any substation - Certificate of fitness to turn on - License to operate electrical installation (If more than 45kW) - Obtain power turn on - Notice of Unit Inspection Completion by Market Support Services Licensee (such as SP group) by EMA for resi with more than 10 units
|  | Clearance requirements (Height) | DSTA/ CAAS | Declaration of as built height
|  | Letterboxes | SingPost | Confirmation and handover of letter boxes
|  | Coordination between Authorities |  | - To resolve conflicts between agencies
|  | Coordination between Consultants |  | - Inter-disciplinary coordination
|  | Client Communication |  | - Review Concept Design, Costs, Regulatory Issues with Client
|  | BIM |  | - Coordinate on BIM model with all relevant parties: Clash detection, design resolution, compliance checks - Integrate BIM model for submission
Compliance Check | Post Completion | Clearance requirements (Main Plan) | BCA | - Amendment BP plan CSC
|  | Clearance requirements (Green Mark) |  | - Green mark verification
|  | Clearance requirements (Fire) | SCDF | FSC
|  | Clearance requirements (Landscape) | NParks | - Completion of planting works in green buffer, roadside planting, open surface car parks - Reinstatement of roadside greenery and other areas under NParks management CSC
|  | Clearance requirements (Road) | LTA R&T | - Post implementation review for TIA - Vesting of road reserve back to LTA CSC
|  | Clearance requirements (Parking) | LTA VP | - Parking inspection - Pedestrian overhead bridges CSC
|  | Clearance requirements (Sewerage & Drainage) | PUB | - Survey plan if less than 300mm from drainage reserve - Leak test on flood barriers CSC
|  | Clearance requirement (Environmental Health) | NEA EH | CSC
|  | Clearance requirements (Industry & Pollution) | NEA PC | CSC
|  | Coordination between Authorities |  | - To resolve conflicts between agencies
|  | Coordination between Consultants |  | - Inter-disciplinary coordination
|  | Client Communication |  | - Review Concept Design, Costs, Regulatory Issues with Client
|  | BIM |  | BIM management
Additional Design Services | Beyond compliance |  |  | Design for Maintainability
| Beyond compliance |  |  | Design for Sustainability (Green Mark Award)
| Beyond compliance |  |  | Design for Sustainability (Super Low, Positive Energy)
| Beyond compliance |  |  | Integrated Digital Delivery (IDD including VDC, BIM)
| Beyond compliance |  |  | Design for Universal Design Index
| Beyond compliance |  |  | Design for Safety (DfS)
| Beyond compliance |  |  | Design for Buildability (PPVC, PBU, Precast)
Duty of Care (Lifetime) |  |  |  | Architect's liability under common law

## 5 BluePrint_Misc
Task | Stage | Component | Relevant Authority | Remarks | Contract. Admin | Compliance . Liabilities | Biz Ops | Design | RESOURCES
BUSINESS OPERATIONS | [8 empty] | Director | Senior Associate | Associate | Senior Architect | Architect | Architectural Executive | BIM Manager | BIM Coordinator | BIM Modeller | Technical Executive
|  | Software Licenses |  | - Any project specific hosting prices
Lithography
Employment Passes
|  | Professional Liability Insurance |  | - Accounts for insurance in face of claims
NEW IN 2024
|  | Active Mobility Checklist | LTA | - Checklist on Active Mobility compliances for QPs
|  | Active Mobility Plan | LTA | - Active Mobility Plan required beyond projects with public housing estates, to include all projects with active mobility elements in the public space
|  | Farm Development Submissions | LTA | - Via lodgement scheme to LTA
|  | Infrastructure Design Criteria | LTA | - New IDC framework for design and construction of various land transport facilities
|  | EV Charging | LTA | - New criteria for buildings to provide EV charging infrastructure